## Project Management Data
Excel Sample Data
Project Management Data
Project Name | Task Name | Assigned to | Start Date | Days Required | End Date | Progress
Marketing | Market Research | Alice | 2024-01-01 | 13 | 2024-01-14 | 78%
Marketing | Content Creation | Bob | 2024-01-14 | 14 | 2024-01-28 | 100%
Marketing | Social Media Planning | Charlie | 2024-01-28 | 22 | 2024-02-19 | 45%
Marketing | Campaign Analysis | Daisy | 2024-02-18 | 25 | 2024-03-14 | 0%
Product Dev | Prototype Development | Ethan | 2024-01-02 | 18 | 2024-01-20 | 100%
Product Dev | Quality Assurance | Fiona | 2024-01-20 | 10 | 2024-01-30 | 78%
Product Dev | User Interface Design | Gabriel | 2024-02-04 | 25 | 2024-02-29 | 0%
Customer Svc | Service Improvement | Hannah | 2024-02-01 | 22 | 2024-02-23 | 100%
Customer Svc | Ticket Resolution | Ian | 2024-02-24 | 25 | 2024-03-20 | 100%
Customer Svc | Customer Feedback | Julia | 2024-03-21 | 30 | 2024-04-20 | 0%
Financial | Budget Analysis | Kevin | 2024-02-02 | 22 | 2024-02-24 | 10%
Financial | Financial Reporting | Mark | 2024-02-13 | 21 | 2024-02-09 | 78%
Financial | Investment Planning | Mark | 2024-03-19 | 25 | 2024-04-13 | 100%
Research | Market Trends Analysis | Nathan | 2024-01-02 | 23 | 2024-01-25 | 50%
Research | Data Collection | Olivia | 2024-01-26 | 32 | 2024-02-27 | 0%
Research | Research Paper Writing | Peter | 2024-02-28 | 27 | 2024-03-26 | 0%
Development | Software Development | Quinn | 2024-01-02 | 36 | 2024-02-07 | 100%
Development | Feature Enhancement | Rachel | 2024-02-08 | 34 | 2024-03-13 | 0%
Development | Code Review | Sam | 2024-03-14 | 30 | 2024-04-13 | 0%
Production | Manufacturing | Tim | 2024-01-03 | 47 | 2024-02-19 | 30%
Production | Quality Control | Ursula | 2024-02-17 | 27 | 2024-03-15 | 0%
Production | Packaging Design | Victor | 2024-03-14 | 22 | 2024-04-05 | 0%
Sales | Lead Generation | Wendy | 2024-01-03 | 60 | 2024-03-03 | 70%
Sales | Client Meetings | Xavier | 2024-01-06 | 20 | 2024-01-26 | 78%
Sales | Contract Negotiation | Yvette | 2024-02-03 | 35 | 2024-03-09 | 0%
Support | Technical Support | Zoe | 2024-01-01 | 25 | 2024-01-26 | 100%
Support | Bug Fixes | Aaron | 2024-01-27 | 31 | 2024-02-27 | 100%
Support | Software Updates | Bella | 2024-03-02 | 22 | 2024-03-24 | 0%
Operations | Process Optimization | Calvin | 2024-01-03 | 30 | 2024-02-02 | 40%
Operations | Inventory Management | Diane | 2024-02-03 | 25 | 2024-02-28 | 0%
Operations | Facility Maintenance | Edward | 2024-02-29 | 20 | 2024-03-20 | 0%
Consulting | Strategic Planning | Fiona | 2024-01-02 | 35 | 2024-02-06 | 60%
Consulting | Market Expansion | Gary | 2024-02-02 | 32 | 2024-03-05 | 0%
Consulting | Client Advisory | Helen | 2024-03-06 | 25 | 2024-03-31 | 0%
Training | Employee Training | Isaac | 2024-01-04 | 27 | 2024-01-31 | 80%
Training | Certification Programs | Jane | 2024-01-28 | 30 | 2024-02-27 | 0%
Training | Skill Development | Kyle | 2024-02-28 | 22 | 2024-03-21 | 0%
Events | Event Planning | Laura | 2024-01-03 | 25 | 2024-01-28 | 30%
Events | Conference Management | Mike | 2024-02-03 | 20 | 2024-02-23 | 0%
Events | Sponsorship Coordinatio | n Nancy | 2024-02-24 | 35 | 2024-03-30 | 0%
Logistics | Supply Chain Management | Oscar | 2024-01-03 | 25 | 2024-01-28 | 50%
Logistics | Transportation Planning | Patricia | 2024-01-29 | 30 | 2024-02-28 | 100%
Logistics | Inventory Optimization | Quentin | 2024-03-29 | 20 | 2024-04-18 | 0%
Engineering | Product Design | Rachel | 2024-01-02 | 25 | 2024-01-27 | 20%
Engineering | System Integration | Sam | 2024-02-02 | 22 | 2024-02-24 | 0%
Engineering | Prototype Testing | Tom | 2024-02-23 | 27 | 2024-03-21 | 0%

## Clean and Transformed Data
Project Name | Task Name | Assigned to | Days Required | Start Date | Start Month | End Date | Progress | Status | Near end
Marketing | Market Research | Alice | 13 | 2026-01-01 | Jan | 2026-01-14 | 78% | Pending | Okay
Marketing | Content Creation | Bob | 14 | 2026-01-14 | Jan | 2026-01-28 | 100% | Completed | Okay
Marketing | Social Media Planning | Charlie | 22 | 2026-01-28 | Jan | 2026-02-19 | 45% | Pending | Okay | TRUE
Marketing | Campaign Analysis | Daisy | 25 | 2026-02-18 | Feb | 2026-03-14 | 0% | Not Started | Close to end
Product Dev | Prototype Development | Ethan | 18 | 2026-01-02 | Jan | 2026-01-20 | 100% | Completed | Okay
Product Dev | Quality Assurance | Fiona | 10 | 2026-01-20 | Jan | 2026-01-30 | 78% | Pending | Okay
Product Dev | User Interface Design | Gabriel | 25 | 2026-02-04 | Feb | 28-02-2026 | 0% | Not Started | Okay
Customer Svc | Service Improvement | Hannah | 22 | 2026-02-01 | Feb | 2026-02-23 | 100% | Completed | Okay
Customer Svc | Ticket Resolution | Ian | 25 | 2026-02-24 | Feb | 2026-03-20 | 100% | Completed | Okay
Customer Svc | Customer Feedback | Julia | 30 | 2026-03-21 | Mar | 2026-04-20 | 0% | Not Started | Close to end
Financial | Budget Analysis | n | 22 | 2026-02-02 | Feb | 2026-02-24 | 10% | Pending | Okay
Financial | Financial Reporting | Mark | 21 | 2026-02-13 | Feb | 2026-03-05 | 78% | Pending | Okay
Financial | Investment Planning | Mark | 25 | 2026-03-19 | Mar | 2026-04-13 | 100% | Completed | Okay
Research | Market Trends Analysis | Nathan | 23 | 2026-01-02 | Jan | 2026-01-25 | 50% | Pending | Okay
Research | Data Collection | Olivia | 32 | 2026-01-26 | Jan | 2026-02-27 | 0% | Not Started | Okay
Research | Research Paper Writing | Peter | 27 | 2026-02-28 | Feb | 2026-03-26 | 0% | Not Started | Close to end
Development | Software Development | Quinn | 36 | 2026-01-02 | Jan | 2026-02-07 | 100% | Completed | Okay
Development | Feature Enhancement | Rachel | 34 | 2026-02-08 | Feb | 2026-03-13 | 0% | Not Started | Close to end
Development | Code Review | Sam | 30 | 2026-03-14 | Mar | 2026-04-13 | 0% | Not Started | Close to end
Production | Manufacturing | Tim | 47 | 2026-01-03 | Jan | 2026-02-19 | 30% | Pending | Okay
Production | Quality Control | Ursula | 27 | 2026-02-17 | Feb | 2026-03-15 | 0% | Not Started | Close to end
Production | Packaging Design | Victor | 22 | 2026-03-14 | Mar | 2026-04-05 | 0% | Not Started | Close to end
Sales | Lead Generation | Wendy | 60 | 2026-01-03 | Jan | 2026-03-03 | 70% | Pending | Okay
Sales | Client Meetings | Xavier | 20 | 2026-01-06 | Jan | 2026-01-26 | 78% | Pending | Okay
Sales | Contract Negotiation | Yvette | 35 | 2026-02-03 | Feb | 2026-03-09 | 0% | Not Started | Close to end
Support | Technical Support | Zoe | 25 | 2026-01-01 | Jan | 2026-01-26 | 100% | Completed | Okay
Support | Bug Fixes | Aaron | 31 | 2026-01-27 | Jan | 2026-02-27 | 100% | Completed | Okay
Support | Software Updates | Bella | 22 | 2026-03-02 | Mar | 2026-03-24 | 0% | Not Started | Close to end
Operations | Process Optimization | Calvin | 30 | 2026-01-03 | Jan | 2026-02-02 | 40% | Pending | Okay
Operations | Inventory Management | Diane | 25 | 2026-02-03 | Feb | 2026-02-28 | 0% | Not Started | Okay
Operations | Facility Maintenance | Edward | 20 | 29-02-2026 | Feb | 2026-03-20 | 0% | Not Started | Close to end
Consulting | Strategic Planning | Fiona | 35 | 2026-01-02 | Jan | 2026-02-06 | 60% | Pending | Okay
Consulting | Market Expansion | Gary | 32 | 2026-02-02 | Feb | 2026-03-05 | 0% | Not Started | Close to end
Consulting | Client Advisory | Helen | 25 | 2026-03-06 | Mar | 2026-03-31 | 0% | Not Started | Close to end
Training | Employee Training | Isaac | 27 | 2026-01-04 | Jan | 2026-01-31 | 80% | Pending | Okay
Training | Certification Programs | Jane | 30 | 2026-01-28 | Jan | 2026-02-27 | 0% | Not Started | Okay
Training | Skill Development | Kyle | 22 | 2026-02-28 | Feb | 2026-03-21 | 0% | Not Started | Close to end
Events | Event Planning | Laura | 25 | 2026-01-03 | Jan | 2026-01-28 | 30% | Pending | Okay
Events | Conference Management | Mike | 20 | 2026-02-03 | Feb | 2026-02-23 | 0% | Not Started | Okay
Events | Sponsorship Coordinatio | Nancy | 35 | 2026-02-24 | Feb | 2026-03-30 | 0% | Not Started | Close to end
Logistics | Supply Chain Management | Oscar | 25 | 2026-01-03 | Jan | 2026-01-28 | 50% | Pending | Okay
Logistics | Transportation Planning | Patricia | 30 | 2026-01-29 | Jan | 2026-02-28 | 100% | Completed | Okay
Logistics | Inventory Optimization | Quentin | 20 | 2026-03-29 | Mar | 2026-04-18 | 0% | Not Started | Close to end
Engineering | Product Design | Rachel | 25 | 2026-01-02 | Jan | 2026-01-27 | 20% | Pending | Okay
Engineering | System Integration | Sam | 22 | 2026-02-02 | Feb | 2026-02-24 | 0% | Not Started | Okay
Engineering | Prototype Testing | Tom | 27 | 2026-02-23 | Feb | 2026-03-21 | 0% | Not Started | Close to end
Formulas:
Near end = IF(AND((TODAY()-[End Date])<=5,[Progress]<=50%),"Close to end","Okay")

## Pivots
Count of Status | Column Labels
Row Labels | Completed
Customer Svc | 22.22%
Development | 11.11%
Financial | 11.11%
Logistics | 11.11%
Marketing | 11.11%
Product Dev | 11.11%
Support | 22.22%
Row Labels | Average of Progress
Customer Svc | 100%
Development | 100%
Financial | 100%
Logistics | 100%
Marketing | 100%
Product Dev | 100%
Support | 100%
Row Labels | Count of Task Name
Close to end | 34.78%
Okay | 65.22%
Average of Days Required | Column Labels
Row Labels | Completed | Not Started | Pending
Consulting |  | 28.5 | 35
Customer Svc | 23.5 | 30
Development | 36 | 32
Engineering |  | 24.5 | 25
Events |  | 27.5 | 25
Financial | 25 |  | 21.5
Logistics | 30 | 20 | 25
Marketing | 14 | 25 | 17.5
Operations |  | 22.5 | 30
Product Dev | 18 | 25 | 10
Production |  | 24.5 | 47
Research |  | 29.5 | 23
Sales |  | 35 | 40
Support | 28 | 22
Training |  | 26 | 27
Row Labels | Count of Task Name
Jan | 21
Feb | 18
Mar | 7
Grand Total | 46
Days Required | (Multiple Items)
Row Labels | Count of Task Name
0% | 8
30% | 1
40% | 1
60% | 1
70% | 1
100% | 3
Grand Total | 15
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Dashboard
Project Management Data Analysis
Project Performance and Risk Analysis Report
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.